## Issed WRF (JCN)
| Location | Scope of Works | Works Request Issuing Date | WRF Status | Works Request Completion Date
1 | Junction of Salisbury Road and Kowloon Park Drive | Enlarging the signal heads of existing traffic lights | 28/02/2023 | No dTAD updated required | 2023-03-27
2 | Junction of Nam Cheong Street and Hai Tan Street | Adjusting existing traffic signals and improving road markings | 21/04/2023 | Issued | 2024-03-25
3 | Junction of Repulse Bay Road and Island Road | Improving traffic signs | 20/03/2023 | Sent to Drawing Office | 02/06/2023
4 | Junction of Tai Chung Road Interchange and Tai Chung Road | Improving traffic signs and road markings | 10/07/2023 | Sent to Drawing Office | 2023-10-19
5 | Junction of Cheung Sha Wan Road and Hing Wah Street | Improving traffic signs and railings | 26/04/2023 | Sent to Drawing Office | 2024-01-30
6 | Junction of Kwan Mun Hau Street, Tsuen Fu Street and Tsuen Wan Market Street | Improving railings | 26/04/2023 | Sent to Drawing Office | 2023-07-12
7 | Junction of Camp Street and Un Chau Street | Improving railings | 30/06/2023 | Sent to Drawing Office | 2023-12-01
8 | Junction of Tsuen Kam Interchange and Wai Tsuen Road | Improving traffic signs, road markings and railings | 31/10/2023 | No dTAD updated required | 2024-03-13
9 | Junction of Tsuen Kam Interchange and Tai Ho Road North | Improving traffic signs | 31/10/2023 | Works in Progress | Works in progress
10 | Junction of Tsuen Kam Interchange and Texaco Road North | Improving traffic signs and railings | 07/11/2023 | Works in Progress | Works in progress
11 | Junction of Cameron Road and Carnarvon Road | Improving railings | 17/11/2023 | Dtad Drawing Updated | 29/01/2024
12 | Junction of Shun Tung Road and Tat Tung Road | Installing additional backing boards at traffic lights | 31/01/2024 | No dTAD updated required | 2024-05-03
13 | Junction of Tai Po Road and Caldecott Road | Improving railings | 15/01/2024 | Works Completed | 2024-08-26
14 | Junction of Shung Wah Street and Wan Wah Street | Improving traffic signs and road markings | 23/02/2024 | Works Completed | 2025-08-19
15 | Junction of Kwun Tong Road and Hong Ning Road | Improving traffic signs | 26/01/2024 | Sent to Drawing Office | 2024-10-26
16 | Junction of Wo Yi Hop Road and Lei Muk Road | Improving railings | 07/02/2024 | Sent to Drawing Office | 2024-06-21
17 | Junction of Fa Yuen Street and Soy Street | Improving traffic signs and road markings | 09/02/2024 | Works Completed | 11/06/2024
18 | Junction of Castle Peak Road and Fuk Wa Street | Improving railings | 25/04/2024 | Sent to Drawing Office | 2025-03-25
19 | Junction of Ap Lei Chau Bridge Road and Lee Nam Road | Improving traffic signs, road markings and railings | 08/03/2024 | Sent to Drawing Office | 25/09/2024
20 | Junction of Castle Peak Road and Cheung Fat Street | Improving railings | 2024-05-17 | Works Completed | 2025-03-27
21 | Junction of Castle Peak Road and Tung Chau West Street | Improving railings | 2024-05-21 | No dTAD updated required | 2024-09-24
22 | Junction of Sha Tsui Road and Tai Chung Road | Improving road markings | 22/05/2024 | No dTAD updated required | 2024-07-26
23 | Junction of Tsuen Kam Interchange and Route Twisk | Improving traffic signs | 06/08/2024 | No dTAD updated required | 2024-11-26
24 | Junction of Wan Chai Road, Cross Street and Tai Wo Street | Improving traffic signs and road markings | 05/06/2024 | Sent to Drawing Office | 19/12/2024
25 | Junction of Morrison Hill Road and Sports Road | Improving traffic signs and narrowing the carriageway | 06/06/2024 | Dtad Drawing Updated | 2024-12-20
26 | Junction of Chung On Street and Shiu Wo Street | Improving traffic signs and road markings | 10/07/2024 | No dTAD updated required | 2024-10-21
27 | Junction of Hing Fong Road and Kwai Yik Road | Improving road markings | 16/07/2024 | Sent to Drawing Office | 2024-08-27
28 | Junction of Princess Margaret Road and Man Fung Path | Improving traffic signs | 08/08/2024 | Sent to Drawing Office | 2025-01-22
29 | Junction of Yen Chow Street and Tung Chau Street | Adjusting existing traffic signals and improving road markings | 19/08/2024 | Sent to Drawing Office | 2025-02-25
30 | Junction of Cheung Sha Wan Road and Lai Chi Kok Road | Improving traffic signs and road markings | 12/12/2024 | Issued | 2025-08-25
31 | Junction of Yen Chow Street and Yee Kuk Street | Adjusting existing traffic signals and improving road markings | 30/09/2024 | Sent to Drawing Office | 2025-02-27
32 | Junction of Haiphong Road and Lock Road | Improving road markings | 30/09/2024 | Dtad Drawing Updated | 30/11/2024
33 | Junction of Kimberley Road and Observatory Road | Improving traffic signs and road markings | 30/09/2024 | Dtad Drawing Updated | 30/11/2024
34 | Tung Chung Eastern Interchange | Improving traffic signs | 29/10/2024 | Sent to Drawing Office | 2025-01-03
35 | Junction of Wo Yi Hop Road and Cheung Wing Road | Improving road markings | 21/11/2024 | Works Completed | 2025-04-09
36 | Junction of Princess Margaret Road and Man Fung Path | Improving traffic signs | 02/01/2025 | Sent to Drawing Office | 2025-03-18
37 | Junction of Sheung Heung Road and Kowloon City Road | Improving traffic signs and road markings | 02/01/2025 | Sent to Drawing Office | 2025-03-14
38 | Junction of Bonham Strand, Hillier Street and Mercer Street | Improving traffic signs and road markings | 23/01/2025 | Dtad Drawing Updated | 12/01/2026
39 | Junction of Castle Peak Road - Tsuen Wan, Kwan Mun Hau Street and Shing Mun Road | Improving road markings | 18/06/2025 | No dTAD updated required | 2025-09-30
40 | Junction of Tsing Yi Heung Sze Wui Road and Chung Mei Road | Improving road markings | 20/06/2025 | Works in Progress | Works in progress
41 | Junction of Clear Water Bay Road and Fung Shing Street | Improving traffic signs | 06/06/2025 | Works Completed | 2026-03-03
42 | Junction of Morrison Hill Road and Sports Road | Improving traffic signs and narrowing the carriageway | 15/07/2025 | Works in Progress | Works in progress
43 | Austin Road near Austin Avenue | Improving railings | 01/09/2025 | Dtad Drawing Updated | 2025-11-25
44 | Junction of Castle Peak Road - Tsuen Wan and Sai Lau Kok Road | Improving road markings | 05/08/2025 | No dTAD updated required | 2026-01-12
45 | Junction of Harbour Road and Fleming Road | Improving traffic signs | 08/10/2025 | Dtad Drawing Updated | 2025-12-01
46 | Junction of Kwai Chung Road, Kwai On Road and Kwai Yik Road | Improving road markings | 27/11/2025 | Sent to Drawing Office | 2026-07-23
47 | Junction of Shui Wo Street and Shui Ning Street | Improving traffic signs | 02/02/2026 | Highway Acknowledged | Works in progress
48 | Junction of Ming Kum Road, Tin King Road and Tsing Tin Road | Improving road markings | 02/04/2026 | Works in Progress | Works in progress
49 | Junction of Nam Cheong Street, Tai Hang Sai Street and Wai Lun Street | Improving traffic signs and railing | 27/04/2026 | Sent to Drawing Office | 26/08/2026
50 | Junction of Hing Ning Road and Hing Fong Road | Improving road markings | 22/06/2026 | Sent to Drawing Office | 23/07/2026
51 | Junction of Lung Cheung Road and Waterloo Road | Improving traffic signs | 8/7/2026 | Issued | 2026-09-12
52 | Junction of Shung Ling Street and Yi Lun Street | Improving traffic signs and railings | 22/7/2026 | Highway Acknowledged | Works in progress
53 | Junction of Queen's Road East and Stubbs Road | Improving railings | 31/7/2026 | Works in Progress | 2026-10-06
54 | Junction of Bonham Road and Pok Fu Lam Road | Improving railings | 31/8/2026 | Sent to Drawing Office | 2026-09-17
55 | Texaco Interchange | Improving traffic signs | 24/09/2026 | Works in Progress | Works in progress
56 | Junction of Cheung Sha Wan Road and Mei Lai Road | Improving railings | 28/09/2026 | Active | Works in progress